## TimeLog
G2 Technology Solutions India Pvt. Ltd.
Log Sheet for Astidian
From | 2020-09-01
To | 2020-09-30
Summarized Timesheet
# | Name | Total Billable Hours
1 | G2 Dev | 120
T O T A L |  | 120
Detailed Timesheet
Date | Day | Dev Name | Task | Billable Dev Hours | Actual hours | Remarks
2020-09-01 | 2020-09-01 | G2 Dev | Tasks Completed: ADS-81 persist delete All flag in the role and able to retrieve. Depending on the flag Delete All button will be made visible/hidden. ADS-85: Table design reviewed and AD change in place, integrations options with HTML canvas to draw signature in progress. Tasks In-Progress: ADS-27: Iframe tenant option revisit. | 6 | 6.5 | Internal review and discussion.
2020-09-02 | 2020-09-02 | G2 Dev | Tasks Completed: ADS-85: Shared zk_ace component setup. ADS-85: Sample signatures which were achieved based on Html canvas shared. Tasks In-Progress ADS-85: Shared zk_ace component review. | 6 | 6
2020-09-03 | 2020-09-03 | G2 Dev | Tasks Completed: ADS-85: Shared zk_ace component ran into compatibility with JDK and later resolved. ADS-85: Able to capture signature in the Attachment window. ADS-93: Unable to save Asset – balance (tab) information àAnalyzed the problem, shared findings and steps to resolve. Tasks In-Progress: ADS-85: Shared zk_ace component review & creating signatures in Pdf attachments. | 8 | 8
2020-09-04 | 2020-09-04 | G2 Dev | Tasks Completed: ADS-85: Signature component integrated with Attachment window to include approval signature in pdf document. ADS-81: Development completed, git feature updated. AD changes in Dev complete. Tasks In-Progress: ADS-85: Signature persistence, file handling. ADS-81: AD changes on Live & Test environments and deployments. | 8 | 8
2020-09-05 | 2020-09-05 | G2 Dev | ADS-85: Signature component – Table design reviewed which will be required to capture User signature in a signature mapping table. And another table to map signatures to the document. DAO design analyzed. | 3 | 3
2020-09-06 | 2020-09-06 | G2 Dev | ADS-85: Signature component – DAO completed to save and retrieve signatures. Also, checks for the document if Meta signature presents so that the last page will be altered accordingly to add or append new signatures. | 4 | 4
2020-09-07 | 2020-09-07 | G2 Dev | ADS-85: Signature component – AD changes completed. DAO approval implemented. Retrieve signatures to update Pdf document as applicable. | 4 | 4
2020-09-08 | 2020-09-08 | G2 Dev | Leave | 0 | 0
2020-09-09 | 2020-09-09 | G2 Dev | Leave | 0 | 0
2020-09-10 | 2020-09-10 | G2 Dev | Tasks Completed: ADS-85: Signature component development completed, reviewed. Git updated. Library compatibility problems resolved. Tasks In-Progress: ADS-81 AD changes on Live & Test environments and deployments. | 8 | 8
2020-09-11 | 2020-09-11 | G2 Dev | Tasks Completed: ADS-85, ADS-81: AD changes sync across Test and Prod environments. ADS-81: Updated PR 76 submitted for review. ADS-85: Git PR comments reviewed to align with Approval and Sign functionalities. Tasks In-Progress: ADS-85: Dev to segregate functions Sign and Approvals. | 8 | 8
2020-09-12 | 2020-09-12 | G2 Dev | ADS-85: Addressed as per comments on prior Pull request to separate logic for Approval status and Signatures. Updated Pdf related changes to PDF project and commons to Base project. | 5 | 5
2020-09-14 | 2020-09-14 | G2 Dev | Tasks Completed: ADS-85: Integrated changes, validations performed. Updated required ant build and classpath. AD updates sync across Test and Live as per the latest changes. Git PR 77 submitted for review, Jira updated. Tasks In-Progress: ADS-81 AD changes on Live & Test environments and deployments (PR pending). | 8 | 8
2020-09-15 | 2020-09-15 | G2 Dev | Tasks Completed: ADS-85: Updated as per comments shared, Signature is captured in AD_User (new binary column added). Merged with latest develop, New Git PR 80 submitted for review, Jira updated. ADS-81: PR submitted and reviewed. Tasks In-Progress: ADS-85: AD changes in Test/Live & deployment (AD_User column change). | 8 | 8
2020-09-16 | 2020-09-16 | G2 Dev | Tasks Completed: ADS-85 & ADS-81: AD changes sync in Test/Live. Deployed to the Test server and WebUI war shared. Jira updates. Tasks In-Progress: ADS-100: Migration of existing DB attachments to DMS. | 8 | 8
2020-09-17 | 2020-09-17 | G2 Dev | Tasks Completed: ADS-92: Zk Ace bootstrap project imported, setup with JDK 7 and tomcat 7 compile issues resolved. Unable to bring the tomcat server up. Tasks In-Progress: ADS-92: Resolve tomcat startup errors. | 6 | 7 | Internal review and discussion.
2020-09-18 | 2020-09-18 | G2 Dev | Tasks Completed: ADS-92: Setup with develop branch to double-check with the feature resolved to build errors but Unable to bring the tomcat server up. (To continue to compare build with Astidian to resolve server startup) Tasks In-Progress: ADS-92: Resolve tomcat startup errors. | 6 | 7 | Internal review and discussion.
2020-09-19 | 2020-09-19 | G2 Dev | ADS-92: Able to setup feature/zk_ace branch with the ace theme. This is set default and the source was not complete. | 4 | 4
2020-09-21 | 2020-09-21 | G2 Dev | Leave | 0 | 0
2020-09-22 | 2020-09-22 | G2 Dev | Tasks Completed: ADS-92: For ace theme setup, took latest develop branch from Astidian components project and made the ace theme switch set at Runtime. Able to view the updated look and feel of the components. Faced Db not in sync as the project has a different DB. Tasks In-Progress: ADS-92: Will continue to import changes to Adsuite project and check the compatibility across mobile/tablets. | 8 | 8
2020-09-23 | 2020-09-23 | G2 Dev | Tasks Completed: ADS-92: Discussions to identify possible options to carry forward new UI implementation. Setup with existing Adsuite – Ace theme, didn’t come up well. UI Components didn’t load properly. Setup with existing Adsuite with Zk v7 and Atlantic v8.6 theme - Again incompatible. Tasks In-Progress: ADS-92: Already ZK v8.6 distribution downloaded (evaluation). Setup Adsuite and check compatibility. | 8 | 8
2020-09-24 | 2020-09-24 | G2 Dev | Tasks Completed: ADS-92: Validated webui against mobile device but the presentation is scrambled and not user friendly (This is with current version, Atlantic theme). Tasks In-Progress: ADS-92: Webui Components to be reviewed. | 4 | 5 | Internal review and discussion.
2020-09-25 | 2020-09-25 | G2 Dev | Leave | 0 | 0
2020-09-28 | 2020-09-28 | G2 Dev | Leave | 0 | 0
2020-09-29 | 2020-09-29 | G2 Dev | Leave | 0 | 0
2020-09-30 | 2020-09-30 | G2 Dev | Leave | 0 | 0
Total Hours |  |  |  | 120 | 123.5
Formulas:
Day = [Date]